## Project Planner
Project Plan - Drawing App
[5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | % COMPLETE | time axis 2022-05-12 to 2022-06-27
 | time axis 2022-05-12 to 2022-06-27
Adapting to new drawing app base | 1 | 3 | 1 | 3 | 100%
Brainstorming extensions | 1 | 7 | 1 | 7 | 100%
Renew drawing tool icons | 4 | 1 | 4 | 1 | 100%
Extensions/Improvements | 5 | 30 | 5 | 30 | 66.67%
Implementing tool size sliders | 5 | 1 | 5 | 1 | 100%
Implementing Undoing/Redoing | 6 | 3 | 6 | 3 | 100%
Implementing Shift key | 9 | 7 | 9 | 3 | 100%
Implementing spacing slider | 16 | 2 | 10 | 2 | 100%
Implementing eraser | 18 | 1 | 18 | 1 | 100%
Report update + code cleanup | 18 | 3 | 18 | 3 | 100%
Implementing Scissors tool | 21 | 3 |  |  | 0%
Improving stamp tool | 23 | 3 |  |  | 0%
Implementing universal mirror | 26 | 3 |  |  | 0%
Implementing 2x colour palette | 29 | 3
Report update + code cleanup | 32 | 3 |  |  | 0%
Midterm submission | 47 | 1 | 47 | 1 | 0%
???
Final submission