## Project Planner
Project Plan - Drawing App
[5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | % COMPLETE | time axis 2022-05-12 to 2022-09-07
 | time axis 2022-05-12 to 2022-09-07
Adapting to new drawing app base | 1 | 3 | 1 | 3 | 100%
Brainstorming extensions | 1 | 7 | 1 | 7 | 100%
Renew drawing tool icons | 4 | 1 | 4 | 1 | 100%
Extensions/Improvements | 5 | 43 | 5 | 43 | 100%
Implementing tool size sliders | 5 | 1 | 5 | 1 | 100%
Implementing Undoing/Redoing | 6 | 3 | 6 | 3 | 100%
Implementing Shift key | 9 | 14 | 9 | 3 | 100%
Implementing spacing slider | 23 | 5 | 12 | 2 | 100%
Report update + code cleanup | 28 | 3 | 15 | 3 | 100%
Implementing Scissors tool | 31 | 3 | 21 | 3 | 100%
Improving stamp tool | 34 | 3 | 27 | 3 | 100%
Midterm submission (code cleanup) | 37 | 11 | 31 | 17 | 100%
Fixing scissors tool | 48 | 5 |  |  | 0%
Implementing 2x colour palette | 53 | 7 |  |  | 0%
Report update + code cleanup | 60 | 30 |  |  | 0%
Debugging, testing, editing code | 90 | 28 |  |  | 0%
Final submission | 118 | 1 |  |  | 100%